## EXAMPLE
PROJECT PLAN
INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | Placement Prediction System |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Job Cloud Job Portal
PROJECT SCOPE | Predicting The Placement Status of Student
PROJECT START DATE | 2024-02-04
PROJECT END DATE | 2024-06-04
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2024-02-04 | 2024-02-10 | 3 | COMPLETED
| 1.2 Recruit a team |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.3 Create a project charter |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.4 Requirement gathering |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
2 Planning
| 2.1 Approval of business process |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
| 2.2 Baseline project plan |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
| 2.3 Team roles and responsibilities |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
3 Execution
| 3.1 Finalize design |  | 2020-12-01 | 20/1/2020 | 8 | COMPLETED
| 3.2 Build |  | 22/1/2020 | 22/3/2020 | 59 | IN PROGRESS
| 3.2.1 Features |  | 22/1/2020 | 31/1/2020 | 9
Registration of candidate and employer
Login for candidate and employer
| Home page layout |  | 2020-01-02 | 2020-10-02 | 10
Navigation bar with logo
Home
Jobs
| Candidates |  | 2020-11-02 | 15/2/2020 | 5
List of candidates with information
| Employer |  | 16/2/2020 | 21/2/2020 | 5
List of employers with information
Advance search bar
Keyoword
Upload resume
Job categories
| Job listing/ Job result page |  | 22/2/2020 | 26/2/2020 | 4
Employer name
Job category & type information
Date & location
Favorite
Apply filter & sort
| Apply for job/ Jobs tag |  | 26/2/2020 | 29/2/2020 | 3
Employer information
Deadline of application
Job details
Job description
Role
Required skills
| Footer |  | 2020-01-03 | 2020-09-03 | 8
Quick links for candidate & employer
Legal and company information
Social media follow
| Profile |  | 2020-10-03 | 15/3/2020 | 5
Dashboard
Job alerts
Applied jobs/Posted jobs
Favorite jobs/candidates
Basic information of candidate/employer
| Post job |  | 16/3/2020 | 22/3/2020 | 7
Job title and desciption
Job category and type
Required skills and application deadline
Salary and qualification
Location
| 3.3 Testing |  | 25/03/2020 | 31/3/2020 | 6
3.3.1 Manual testing
3.3.2 Automation testing
| 4 Closure |  | 2020-01-04 | 2020-01-04 | 1